## Sheet1
Assignment 3
Task | Work Size | Productivity Rate | Duration with 1 ppl(hours) | Duration with 1 ppl(hours) | Total ppl | Duration (days)
Project Plan
Write Plan | 157 | 3.5 | 44.8571 | 45 | 1 | 5.625
Review Plan
Preparation for Review | 157 | 5 | 31.4 | 32 | 9 | 0.44444
Review Meeting | 157 | 10 | 15.7 | 16 | 9 | 0.22222
Rework | 101 | 7 | 14.4286 | 15 | 1 | 1.875
Documented Software Development Process Updates
Process Changes | 96 | 2 | 48 | 48 | 6 | 1
Review Changes
Preparation for Review | 96 | 5 | 19.2 | 20 | 6 | 0.41667
Review Meeting | 96 | 10 | 9.6 | 10 | 6 | 0.20833
Rework | 37 | 5 | 7.4 | 8 | 6 | 0.16667
Requirement
Write Requirements | 178 | 3.5 | 50.8571 | 51 | 1 | 6.375
Review Requirements
Preparation for Review | 178 | 15 | 11.8667 | 12 | 4 | 0.375
Review Meeting | 178 | 20 | 8.9 | 9 | 5 | 0.225
Rework | 159 | 5 | 31.8 | 32 | 1 | 4
Build the development and testing lab environment
Hardware Environment
Servers | 12 | 0.125 | 96 | 96 | 1 | 12
Clients | 27 | 0.625 | 43.2 | 44 | 1 | 5.5
Software Development Tools
Build/Compile Tools | 8 | 1 | 8 | 8 | 1 | 1
Software Testing Tools
Test Cases Execution Tools | 7 | 0.25 | 28 | 28 | 1 | 3.5
Simulation Tools | 12 | 0.25 | 48 | 48 | 1 | 6
Analysis
Write Analysis Document | 136 | 2.5 | 54.4 | 55 | 1 | 6.875
Review Analysis Document
Preparation for Analysis Document | 136 | 2.5 | 54.4 | 55 | 4 | 1.7188
Review Meeting | 136 | 5 | 27.2 | 28 | 5 | 0.7
Rework | 58 | 3.5 | 16.5714 | 17 | 1 | 2.125
Design
Write DD | 163 | 2.5 | 65.2 | 66 | 3 | 2.75
Review DD
Preparation for DD | 163 | 5 | 32.6 | 33 | 4 | 1.0312
Review Meeting | 163 | 9 | 18.1111 | 19 | 5 | 0.475
Rework | 126 | 4.5 | 28 | 28 | 3 | 1.1667
Coding
Write Code | 3987 | 5 | 797.4 | 798 | 2 | 49.875
Unit Testing
Prepare/Execute Test Cases | 407 | 1.625 | 250.4615 | 251 | 2 | 15.6875
Fix Found Defects | 327 | 1.75 | 186.8571 | 187 | 2 | 11.6875
Test Fixed Defects | 327 | 3.75 | 87.2 | 88 | 2 | 5.5
Code Inspection
Preparation for Code Inspection | 3987 | 125 | 31.896 | 32 | 2 | 2
Code Inspection Meeting | 3987 | 175 | 22.7829 | 23 | 2 | 1.4375
Rework | 323 | 4.5 | 71.7778 | 72 | 2 | 4.5
Testing
Write Test Plan (TP) | 173 | 1.25 | 138.4 | 139 | 8 | 2.1719
Review TP | [5 empty] | #DIV/0!
Preparation for TP | 173 | 4 | 43.25 | 44 | 7 | 0.78571
Review TP Meeting | 173 | 10 | 17.3 | 18 | 7 | 0.32143
Rework | 98 | 5 | 19.6 | 20 | 7 | 0.35714
Execute TP (test cases) | 189 | 1.5 | 126 | 126 | 7 | 2.25
Fix Found Defects | 72 | 1.25 | 57.6 | 58 | 7 | 1.0357
Test Fixed Defects | 72 | 1.875 | 38.4 | 39 | 7 | 0.69643
Documentation
User Documentation | 160 | 3.5 | 45.7143 | 46 | 1 | 5.75
Review UD
Preparation for UD Review | 160 | 5 | 32 | 32 | 4 | 1
Review UD Meeting | 160 | 9 | 17.7778 | 18 | 5 | 0.45
Rework | 189 | 10 | 18.9 | 19 | 1 | 2.375

## Sheet2
Assignment 1 |  |  | Assignment 2 |  |  | Assignment 3
Task | Work Size | Productivity Rate | Task | Work Size | Productivity Rate | Task | Work Size | Productivity Rate
Project Plan |  |  | Project Plan |  |  | Project Plan
Write Plan | 83 | 2 | Write Plan | 95 | 5 | Write Plan | 157 | 3.5
Review Plan |  |  | Review Plan |  |  | Review Plan
Preparation for Review |  | 5 | Preparation for Review |  | 5 | Preparation for Review |  | 5
Review Meeting |  | 10 | Review Meeting |  | 10 | Review Meeting |  | 10
Rework | 49 | 10 | Rework | 66 | 4 | Rework | 101 | 7
Risk Mitigation and Contingency Plan | [5 empty] | Documented Software Development Process Updates
Write Plan | 22 | 2 |  |  |  | Process Changes | 96 | 2
Review Plan | [5 empty] | Review Changes
Preparation for review |  | 5 |  |  |  | Preparation for Review |  | 5
Review Meeting |  | 10 |  |  |  | Review Meeting |  | 10
Rework | 37 | 4 |  |  |  | Rework | 37 | 5
Requirement |  |  | Requirement |  |  | Requirement
Write Requirements | 117 | 2 | Write Requirements | 312 | 5 | Write Requirements | 178 | 3.5
Write Use Case Model | 98 | 0.25
Review Requirements/ Use Case Model |  |  | Review Requirements |  |  | Review Requirements
prepration for review(req) |  | 25 | Preparation for Review |  | 5 | Preparation for Review |  | 15
prepration for review(use case) |  | 5
Review Meeting(req) |  | 30 | Review Meeting |  | 10 | Review Meeting |  | 20
Review Meeting(use case) |  | 10
Rework | 137 | 5 | Rework | 190 | 5 | Rework | 159 | 5
|  |  | Lab and Environment Setup |  |  | Build the development and testing lab environment
|  |  | Hardware |  |  | Hardware Environment
|  |  | Install Network Elements |  |  | Servers | 12 | 0.125
|  |  | Routers | 2 | 0.25 | Clients | 27 | 0.625
|  |  | Bridge | 4 | 0.25 | Software Development Tools
|  |  | Install Server | 10 | 0.125 | Build/Compile Tools | 8 | 1
|  |  | Install Clients | 110 | 1.25 | Software Testing Tools
|  |  | Software |  |  | Test Cases Execution Tools | 7 | 0.25
|  |  | Install Development Tools | 32 | 0.5 | Simulation Tools | 12 | 0.25
|  |  | Install Testing Tools | 21 | 0.5
Analysis | [5 empty] | Analysis
Write Analysis Document | 129 | 5 |  | 0 |  | Write Analysis Document | 136 | 2.5
Review Analysis Document | [5 empty] | Review Analysis Document
Preparation for Analysis Document |  | 5 |  |  |  | Preparation for Analysis Document |  | 2.5
Review Meeting |  | 10 |  |  |  | Review Meeting |  | 5
Rework | 55 | 7 |  | 0 |  | Rework | 58 | 3.5
Design |  |  | Analysis/Design Document |  |  | Design
Write DD | 217 | 2 | Write DD | 290 | 3 | Write DD | 163 | 2.5
Review DD |  |  | Review DD |  |  | Review DD
Preparation for DD |  | 5 | Preparation for DD |  | 5 | Preparation for DD |  | 5
Review Meeting |  | 8 | Review Meeting |  | 10 | Review Meeting |  | 9
Rework | 193 | 5 | Rework | 189 | 4 | Rework | 126 | 4.5
Data Model
Write Data Model (DM) | 50 | 0.2 | Create Data Model | 34 | 1
Review DM |  |  | Review Data Model
Preparation for DM |  | 3 | Preparation for DM |  | 5
Review Meeting |  | 6 | Review Meeting |  | 10
Rework | 94 | 5 | Rework | 189 | 4
Coding and unit test |  |  | Coding and unit test |  |  | Coding
Write Code | 5100 | 5 | Write Code | 7410 | 5 | Write Code | 3987 | 5
Unit Testing |  |  | Unit Testing |  |  | Unit Testing
Prepare/Execute Test Cases | 324 | 1.25 | Prepare/Execute Test Cases | 1023 | 2 | Prepare/Execute Test Cases | 407 | 1.625
Fix Found Defects | 210 | 1 | Fix Found Defects | 892 | 2.5 | Fix Found Defects | 327 | 1.75
Test Fixed Defects | 210 | 1.25 | Test Fixed Defects | 892 | 6.25 | Test Fixed Defects | 327 | 3.75
Code Inspection |  |  | Code Inspection |  |  | Code Inspection
Preparation for Code Inspection |  | 150 | Preparation for Code Inspection |  | 100 | Preparation for Code Inspection |  | 125
Code Inspection Meeting |  | 200 | Code Inspection Meeting |  | 150 | Code Inspection Meeting |  | 175
Rework | 167 | 5 | Rework | 947 | 4 | Rework | 323 | 4.5
Testing |  |  | Testing |  |  | Testing
Write Test Plan (TP) | 190 | 0.625 | Write Test Plan (TP) | 284 | 1.25 | Write Test Plan (TP) | 173 | 1.25
Review TP |  |  | Review TP |  |  | Review TP
Preparation for TP |  | 5 | Preparation for TP |  | 5 | Preparation for TP |  | 4
Review TP Meeting |  | 10 | Review TP Meeting |  | 10 | Review TP Meeting |  | 10
Rework | 192 | 5 | Rework | 266 | 4 | Rework | 98 | 5
Execute TP (test cases) | 258 | 0.625 | Execute TP (test cases) | 442 | 1 | Execute TP (test cases) | 189 | 1.5
Fix Found Defects | 188 | 1.25 | Fix Found Defects | 201 | 0.625 | Fix Found Defects | 72 | 1.25
Test Fixed Defects | 188 | 0.625 |  |  |  | Test Fixed Defects | 72 | 1.875
Documentation |  |  | Documentation |  |  | Documentation
User Documentation | 190 | 2 | User Documentation | 297 | 5 | User Documentation | 160 | 3.5
Review UD |  |  | Review UD |  |  | Review UD
Preparation for UD Review |  | 5 | Preparation for UD Review Meeting |  | 5 | Preparation for UD Review |  | 5
Review UD Meeting |  | 10 | Review UD Meeting |  | 8 | Review UD Meeting |  | 9
Rework | 245 | 12 | Rework | 283 | 8 | Rework | 180 | 10
Training
|  |  | Training Handouts (TH) | 90 | 1
Review Training Handouts (TH)
|  |  | Preparation for TH review meeting |  | 5
|  |  | Review TH Meeting |  | 8
|  |  | Rework | 193 | 8
0.15625